## Sheet1
ID | Task | Parent | Depends | ?
102 | Support and Documentation
81 | Document cwru_ros_pkg | 102
82 | cwru_ros_pkg wiki (github) | 81
83 | cwru_ros_pkg doxygen | 81
103 | Document robot | 102
89 | Document ABB Driver | 102 | 7
90 | ABB Driver wiki | 89
91 | ABB Driver doxygen | 89
104 | Send ABB driver to SWRI | 8 | 7
84 | Project Blog | 102
85 | Gantt Chart | 102
86 | Videos | 102
87 | Waypoint video | 86 | 14
88 | ROS-controlled arm video | 86 | 12
89 | Carrier Manipulation video | 86 | 12
90 | Pick and place video | 86 | 96 | ?
91 | Door traversal video | 86
87 | Thesis | 102 | 12,13,14,92
88 | Conference Paper on mobile manipulation planner | 102 | 94
93 | Clean launch files | 102
105 | Simulation and logging
30 | Gazebo | 105
31 | Create Robot Model | 30 | 26
35 | Arm Nav Warehouse | 105 | 9
100 | Learn how to use arm nav warehouse | 35
101 | Create/modify launch files to use arm nav warehouse for testing arm driver/planning | 35
36 | Rviz | 105 | 9
99 | Create/modify launch files for live rviz | 36
37 | ROS Bag | 105
97 | Create/modify launch files for bag recording | 37
98 | Create launch files for bag playback | 37
12 | Arm Control
7 | ABB ROS Driver | 12
57 | RAPID TCP Server | 7
58 | RAPID joint position commander | 7 | 57
59 | RAPID tool position commander | 7 | 57
63 | RAPID gripper I/O commander | 7 | 57
64 | ROS TCP client | 7
8 | ROS Industrial | 12 | 7, 9
9 | Arm Navigation | 12
26 | Fully Defined URDFs | 9
27 | Finalize CAD | 26 | 28
29 | Collision meshes | 26 | 27
32 | Visualization meshes | 26 | 27
33 | Arm nav stack | 9 | 26
34 | Arm joint limits | 33
100 | Investigate arm motion planners | 33
101 | Choose and tune arm motion planner | 33 | 100
92 | Choreographed Motion |  | 12, 14
93 | Read up on mobile manipulators (esp in ROS) | 92
94 | Design architecture of coordinated planning node (steal from PR2?) | 92
95 | Implement coordinated planning node | 92 | 94
96 | Pick and place script/command | 92 | 95
13 | E-stop
19 | Respin E-stop remote | 13 | 20 | ?
53 | E-stop remote schematic | 13
54 | E-stop remote layout | 13 | 53
55 | Order E-stop remote parts | 13 | 54
56 | Assemble E-stop remote | 13 | 55
20 | New E-stop remote case | 13
106 | Physical
10 | Front Kinect | 106
65 | 2 more standoffs (1 short, 1 long) | 10
66 | Kinect mounting bracket (front) | 10
67 | Mount and wire front kinect | 10 | 65,66
72 | Rear Kinect | 106 |  | ?
73 | Kinect mounting bracket (rear) | 72
74 | Order PCI-E USB Controller | 72
75 | Mount and wire rear Kinect | 72 | 73,74,65
11 | Camera | 106 | ?
70 | Mount and wire camera | 11 | 71
71 | Figure out where to mount camera | 11
21 | Onboard Carrier | 106
22 | Design onboard carrier | 21
23 | Order parts for onboard carrier | 21 | 22
24 | Fabricate onboard carrier | 21 | 23
25 | Mount onboard carrier | 21 | 24
28 | Raise arm
107 | Perception
68 | Kinect processing chain | 107
76 | Kinect point cloud to octomap for collision avoidance/arm planning | 107 | 68
77 | Manipulable object recognition using Kinect/vision | 107 | 68,69
69 | Vision processing | 107 | 11
6 | Respin E-stop receiver | 13
41 | E-stop receiver schematic | 6 | 5
42 | E-stop receiver layout | 6 | 41
43 | Order E-stop receiver parts | 6 | 42
44 | Assemble E-stop receiver | 6 | 43
45 | E-stop receiver case | 6 | 44
5 | Better xBee Power | 13
39 | Bench test xBee | 5
40 | Design new power supply/caps | 5 | 39
46 | Verify xBee power supply on bench | 5 | 40
47 | Verify remote E-stop on robot | 5 | 46
4 | E-stop arm | 13
48 | Test relay | 4
49 | Install/wire relay | 4 | 48
108 | Response to arm stops | 13 |  | ?
50 | Add e-stop state to I/O in RAPID | 108
51 | Wire e-stop I/O into e-stop receiver | 108
52 | Test e-stop from IRC5 | 108 | 51
14 | Nav
1 | Steering function | 14
15 | Characterize drive base limits | 1
16 | Research steering function possibilities | 1
17 | Pick a steering function (or combination of them) | 1 | 16
18 | Tune steering | 1 | 17
2 | Map localization | 14
80 | Get AMCL working | 2
3 | 3d Map | 14 | 68
79 | Refactor precision steering to use octomapping | 14
78 | 2d map (from octomap?) | 14 | 3