## Sheet1
ID | Task | Parent | Depends | ? | Leaf | Complete | Active
1 | Steering function | 14 |  |  | FALSE | FALSE | FALSE
2 | Map localization | 14 |  |  | FALSE | FALSE | FALSE
3 | 3d Map | 14 | 68 |  | TRUE | FALSE | FALSE
4 | E-stop arm | 13 |  |  | FALSE | FALSE | FALSE
5 | Better xBee Power | 13 |  |  | FALSE | FALSE | FALSE
6 | Respin E-stop receiver | 13 |  |  | FALSE | FALSE | FALSE
7 | ABB ROS Driver | 12 |  |  | FALSE | FALSE | FALSE
8 | ROS Industrial | 12 | 7,9 |  | FALSE | FALSE | #N/A
9 | Arm Navigation | 12 |  |  | FALSE | FALSE | FALSE
10 | Front Kinect | 106 |  |  | FALSE | FALSE | FALSE
11 | Camera | 106 |  | ? | FALSE | FALSE | FALSE
12 | Arm Control |  |  |  | FALSE | FALSE | FALSE
13 | E-stop |  |  |  | FALSE | FALSE | FALSE
14 | Nav |  |  |  | FALSE | FALSE | FALSE
15 | Characterize drive base limits | 1 |  |  | TRUE | TRUE | FALSE
16 | Research steering function possibilities | 1 |  |  | TRUE | FALSE | TRUE
17 | Pick a steering function (or combination of them) | 1 | 16 |  | TRUE | FALSE | FALSE
18 | Tune steering | 1 | 17 |  | TRUE | FALSE | FALSE
19 | Respin E-stop remote | 13 | 20 |  | TRUE | FALSE | FALSE
20 | New E-stop remote case | 13 |  |  | TRUE | FALSE | TRUE
21 | Onboard Carrier | 106 |  |  | FALSE | FALSE | FALSE
22 | Design onboard carrier | 21 |  |  | TRUE | FALSE | TRUE
23 | Order parts for onboard carrier | 21 | 22 |  | TRUE | FALSE | FALSE
24 | Fabricate onboard carrier | 21 | 23 |  | TRUE | FALSE | FALSE
25 | Mount onboard carrier | 21 | 24 |  | TRUE | FALSE | FALSE
26 | Fully Defined URDFs | 9 |  |  | FALSE | FALSE | FALSE
27 | Finalize CAD | 26 | 28 |  | TRUE | FALSE | FALSE
28 | Raise arm |  |  |  | TRUE | FALSE | TRUE
29 | Collision meshes | 26 | 27 |  | TRUE | FALSE | FALSE
30 | Gazebo | 105 |  |  | FALSE | FALSE | FALSE
31 | Create Robot Model | 30 | 26 |  | TRUE | FALSE | FALSE
32 | Visualization meshes | 26 | 27 |  | TRUE | FALSE | FALSE
33 | Arm nav stack | 9 | 26 |  | FALSE | FALSE | FALSE
34 | Arm joint limits | 33 |  |  | TRUE | TRUE | FALSE
35 | Arm Nav Warehouse | 105 | 9 |  | FALSE | FALSE | FALSE
36 | Rviz | 105 | 9 |  | FALSE | FALSE | FALSE
37 | ROS Bag | 105 |  |  | FALSE | FALSE | FALSE
39 | Bench test xBee | 5 |  |  | TRUE | FALSE | TRUE
40 | Design new power supply/caps | 5 | 39 |  | TRUE | FALSE | FALSE
41 | E-stop receiver schematic | 6 | 5 |  | TRUE | FALSE | FALSE
42 | E-stop receiver layout | 6 | 41 |  | TRUE | FALSE | FALSE
43 | Order E-stop receiver parts | 6 | 42 |  | TRUE | FALSE | FALSE
44 | Assemble E-stop receiver | 6 | 43 |  | TRUE | FALSE | FALSE
45 | E-stop receiver case | 6 | 44 |  | TRUE | FALSE | FALSE
46 | Verify xBee power supply on bench | 5 | 40 |  | TRUE | FALSE | FALSE
47 | Verify remote E-stop on robot | 5 | 46 |  | TRUE | FALSE | FALSE
48 | Test relay | 4 |  |  | TRUE | FALSE | TRUE
49 | Install/wire relay | 4 | 48 |  | TRUE | FALSE | FALSE
50 | Add e-stop state to I/O in RAPID | 108 |  | ? | TRUE | FALSE | TRUE
51 | Wire e-stop I/O into e-stop receiver | 108 |  | ? | TRUE | FALSE | TRUE
52 | Test e-stop from IRC5 | 108 | 51 | ? | TRUE | FALSE | FALSE
53 | E-stop remote schematic | 13 |  | ? | TRUE | FALSE | TRUE
54 | E-stop remote layout | 13 | 53 |  | TRUE | FALSE | FALSE
55 | Order E-stop remote parts | 13 | 54 |  | TRUE | FALSE | FALSE
56 | Assemble E-stop remote | 13 | 55 |  | TRUE | FALSE | FALSE
57 | RAPID TCP Server | 7 |  |  | TRUE | TRUE | FALSE
58 | RAPID joint position commander | 7 | 57 |  | TRUE | TRUE | FALSE
59 | RAPID tool position commander | 7 | 57 | ? | TRUE | FALSE | TRUE
63 | RAPID gripper I/O commander | 7 | 57 |  | TRUE | FALSE | TRUE
64 | ROS TCP client | 7 |  |  | TRUE | TRUE | FALSE
65 | 2 more standoffs (1 short, 1 long) | 10 |  |  | TRUE | TRUE | FALSE
66 | Kinect mounting bracket (front) | 10 |  |  | TRUE | FALSE | TRUE
67 | Mount and wire front kinect | 10 | 65,66 |  | TRUE | FALSE | #N/A
68 | Kinect processing chain | 107 | 67 | ? | TRUE | FALSE | FALSE
69 | Vision processing | 107 | 11 | ? | TRUE | FALSE | FALSE
70 | Mount and wire camera | 11 | 71 | ? | TRUE | FALSE | FALSE
71 | Figure out where to mount camera | 11 |  | ? | TRUE | FALSE | TRUE
72 | Rear Kinect | 106 |  | ? | FALSE | FALSE | FALSE
73 | Kinect mounting bracket (rear) | 72 |  | ? | TRUE | FALSE | TRUE
74 | Order PCI-E USB Controller | 72 |  | ? | TRUE | FALSE | TRUE
75 | Mount and wire rear Kinect | 72 | 73,74,65 | ? | TRUE | FALSE | #N/A
76 | Kinect point cloud to octomap for collision avoidance/arm planning | 107 | 68 | ? | TRUE | FALSE | FALSE
77 | Manipulable object recognition using Kinect/vision | 107 | 68,69 |  | TRUE | FALSE | #N/A
78 | 2d map (from octomap?) | 14 | 3 |  | TRUE | FALSE | FALSE
79 | Refactor precision steering to use octomapping | 14 |  |  | TRUE | FALSE | TRUE
80 | Get AMCL working | 2 |  |  | TRUE | FALSE | TRUE
81 | Document cwru_ros_pkg | 102 |  |  | FALSE | FALSE | FALSE
82 | cwru_ros_pkg wiki (github) | 81 |  |  | TRUE | FALSE | TRUE
83 | cwru_ros_pkg doxygen | 81 |  |  | TRUE | FALSE | TRUE
84 | Project Blog | 102 |  |  | TRUE | FALSE | TRUE
86 | Videos | 102 |  |  | FALSE | FALSE | FALSE
87 | Waypoint video | 86 | 14 |  | TRUE | FALSE | FALSE
87 | Thesis | 102 | 12,13,14,92 |  | TRUE | FALSE | #N/A
88 | ROS-controlled arm video | 86 | 12 |  | TRUE | FALSE | FALSE
88 | Conference Paper on mobile manipulation planner | 102 | 94 |  | TRUE | FALSE | FALSE
89 | Document ABB Driver | 102 | 7 |  | FALSE | FALSE | FALSE
89 | Carrier Manipulation video | 86 | 12 |  | FALSE | FALSE | FALSE
90 | Pick and place video | 86 | 96 | ? | TRUE | FALSE | FALSE
90 | ABB Driver wiki | 89 |  |  | TRUE | FALSE | TRUE
91 | ABB Driver doxygen | 89 |  |  | TRUE | TRUE | FALSE
91 | Door traversal video | 86 | 14 |  | TRUE | FALSE | FALSE
92 | Choreographed Motion |  | 12,14 |  | FALSE | FALSE | #N/A
93 | Clean launch files | 102 |  |  | TRUE | FALSE | TRUE
93 | Read up on mobile manipulators (esp in ROS) | 92 |  |  | TRUE | FALSE | TRUE
94 | Design architecture of coordinated planning node (steal from PR2?) | 92 |  |  | TRUE | FALSE | TRUE
95 | Implement coordinated planning node | 92 | 94 |  | TRUE | FALSE | FALSE
96 | Pick and place script/command | 92 | 95 |  | TRUE | FALSE | FALSE
97 | Create/modify launch files for bag recording | 37 |  |  | TRUE | FALSE | TRUE
98 | Create launch files for bag playback | 37 |  |  | TRUE | FALSE | TRUE
99 | Create/modify launch files for live rviz | 36 |  |  | TRUE | FALSE | TRUE
100 | Learn how to use arm nav warehouse | 35 |  |  | TRUE | FALSE | TRUE
100 | Investigate arm motion planners | 33 |  |  | TRUE | FALSE | TRUE
101 | Choose and tune arm motion planner | 33 | 100 |  | TRUE | FALSE | FALSE
101 | Create/modify launch files to use arm nav warehouse for testing arm driver/planning | 35 |  |  | TRUE | FALSE | TRUE
102 | Support and Documentation |  |  |  | FALSE | FALSE | FALSE
103 | Document robot | 102 |  |  | TRUE | FALSE | TRUE
104 | Send ABB driver to SWRI | 8 | 7 |  | TRUE | FALSE | FALSE
105 | Simulation and logging |  |  |  | FALSE | FALSE | FALSE
106 | Physical |  |  |  | FALSE | FALSE | FALSE
107 | Perception |  |  |  | FALSE | FALSE | FALSE
108 | Response to arm stops | 13 |  | ? | FALSE | FALSE | FALSE
109 | Battery Performance Specs | 102 |  |  | FALSE | FALSE | FALSE
110 | Battery performance - arm motion | 109 |  |  | TRUE | FALSE | TRUE
111 | Battery performance - drivetrain motion | 109 |  |  | TRUE | FALSE | TRUE
112 | Battery performance - baseline | 109 |  |  | TRUE | FALSE | TRUE
113 | Battery performance - arm on, not moving | 109 |  |  | TRUE | FALSE | TRUE
114 | Arm/Camera Calibration (Kinect) | 107 | 68 |  | TRUE | FALSE | FALSE
115 | Figure out why cRIO voltage reads 0 and fix | 106 |  | ? | TRUE | FALSE | TRUE
116 | PC Power Supply auto-boot | 106 |  | ? | TRUE | FALSE | TRUE